## Worksheet
Project Timeline
Project Name | alpha
Start Date | 2024-08-01
End Date | 2024-08-31
Framework | Agile
Phase | Start Date | End Date | Details | Completed
Planning and Requirements Gathering | 2024-08-01 | 2024-08-08 | Market Research: Identify audience and competitors. Feature Prioritization: List core features and create backlog. Scope Definition: Outline project goals and boundaries. Team Formation: Assemble required team members. | FALSE
Design and Prototyping | 2024-08-08 | 2024-08-15 | Information Architecture: Plan content and navigation. Wireframing: Create screen layouts. UI/UX Design: Develop design and user experience. Prototyping: Build interactive models for feedback. | FALSE
Development | 2024-08-15 | 2024-08-29 | Sprint Planning: Break project into sprints. Development: Write code for features. Continuous Integration: Regularly integrate code. Testing: Conduct unit and integration testing. | FALSE
Testing and Quality Assurance | 2024-08-29 | 2024-09-05 | Functional Testing: Ensure features work. Performance Testing: Test speed and stability. Security Testing: Check for vulnerabilities. Usability Testing: Collect user feedback. | FALSE
Deployment and Release | 2024-09-05 | 2024-08-31 | App Store Submission: Submit to the app store. Launch Marketing: Promote the app. Post-Launch Support: Provide support and fix issues. | FALSE
Maintenance and Updates | 2024-08-31 | 2024-10-01 | Bug Fixing: Address reported issues. Feature Updates: Add new features. Performance Optimization: Improve app performance. Security Patches: Fix security issues. | FALSE